## Summary
ProjectName | ProjectTitle | ProjectFile | PlannedStart | PlannedFinish | LastSaved | OverallPercentComplete | TotalTasks | OpenActions | CriticalOpenActions | LateOpenActions
Schedule - Parker Laboratories Gel Packet.xml | Project Schedule Parker Gel Packet | Schedule - Parker Laboratories Gel Packet.xml | 2023-07-04 08:00 | 2026-03-09 17:00 | 2025-11-14 10:36 | 70.2 | 57 | 17 | 6 | 6
18.02.003 Project Timeline.xml | 18.02.003 Project Timeline | 18.02.003 Project Timeline.xml | 2025-07-07 08:00 | 2026-03-03 17:00 | 2025-11-14 10:37 | 58.4 | 237 | 101 | 23 | 35
20250107-001 Full Schedule.xml | Full Schedule | 20250107-001 Full Schedule.xml | 2024-12-16 08:00 | 2027-12-01 17:00 | 2025-11-14 10:38 | 45.6 | 474 | 245 | 8 | 152
QP 20250422-001 Project Schedule.xml | Philips NG3DEV Reusable Endoguide | QP 20250422-001 Project Schedule.xml | 2025-04-22 08:00 | 2025-12-09 17:00 | 2025-11-14 10:39 | 0 | 35 | 35 | 8 | 33

## TopOpenActions
Project | TaskUID | TaskName | PercentComplete | Critical | Start | Finish | Notes
Schedule - Parker Laboratories Gel Packet.xml | 133 | Route VR (VR 9.0-221-02) for approval via Promotion Request | 0 | TRUE | 2025-11-04 08:00 | 2025-11-10 17:00 | PR #: See note above for other VR 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions.
Schedule - Parker Laboratories Gel Packet.xml | 132 | Route VR for Bioburden (PR 9.0-221-01) for approval via Promotion Request | 0 | TRUE | 2025-11-04 08:00 | 2025-11-10 17:00 | 8/1/2025: have continually reached out to Ronda to ask for updates. Also have communicated with Kasi regarding updates when she visited them. Parker has not sent any correspondance between December 2024 and July 16, 2025. New materials are set to release in October this year. I told Ronda we still needed the follwing (in black) from them to close out our documentation. Their responses are in RED. Responses from Candy at Parker (cbeck@parkerlabs.com) 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions.
Schedule - Parker Laboratories Gel Packet.xml | 128 | Update Quality Records | 0 | TRUE | 2025-11-11 08:00 | 2025-12-15 17:00
Schedule - Parker Laboratories Gel Packet.xml | 127 | Complete Quality Plan summary report | 0 | TRUE | 2025-12-16 08:00 | 2026-01-12 17:00
Schedule - Parker Laboratories Gel Packet.xml | 131 | Project Complete | 0 | TRUE | 2026-03-09 17:00 | 2026-03-09 17:00
Schedule - Parker Laboratories Gel Packet.xml | 130 | Release updated quality records via CN | 0 | TRUE | 2026-01-13 08:00 | 2026-03-09 17:00
Schedule - Parker Laboratories Gel Packet.xml | 134 |  | 0 | FALSE | 2023-07-04 08:00 | 2023-07-04 17:00
Schedule - Parker Laboratories Gel Packet.xml | 139 | Complete Quality Plan summary report | 0 | FALSE | 2025-10-27 08:00 | 2025-11-07 17:00
Schedule - Parker Laboratories Gel Packet.xml | 54 | Route VR (VR 9.0-221-02) for approval via Promotion Request | 0 | FALSE | 2025-11-04 08:00 | 2025-11-10 17:00 | PR #: See note above for other VR 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions.
Schedule - Parker Laboratories Gel Packet.xml | 42 | Route VR for Bioburden (VR 9.0-221-01) for approval via Promotion Request | 0 | FALSE | 2025-11-04 08:00 | 2025-11-10 17:00 | 8/1/2025: have continually reached out to Ronda to ask for updates. Also have communicated with Kasi regarding updates when she visited them. Parker has not sent any correspondance between December 2024 and July 16, 2025. New materials are set to release in October this year. I told Ronda we still needed the follwing (in black) from them to close out our documentation. Their responses are in RED. Responses from Candy at Parker (cbeck@parkerlabs.com) 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions.
18.02.003 Project Timeline.xml | 404 | 134-200-2 Adj | 0 | TRUE | 2025-10-21 08:00 | 2025-11-06 17:00
18.02.003 Project Timeline.xml | 407 | Ship T2 Samples | 0 | TRUE | 2025-11-07 08:00 | 2025-11-11 17:00
18.02.003 Project Timeline.xml | 408 | T2 ES (Testing) | 0 | TRUE | 2025-11-12 08:00 | 2025-11-18 17:00
18.02.003 Project Timeline.xml | 409 | T2 Sample Approval | 0 | TRUE | 2025-11-18 17:00 | 2025-11-18 17:00
18.02.003 Project Timeline.xml | 411 | 134-200-1 | 0 | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00
18.02.003 Project Timeline.xml | 412 | 134-200-2 | 0 | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00
18.02.003 Project Timeline.xml | 413 | 134-200-3 | 0 | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00
18.02.003 Project Timeline.xml | 416 | Receive Tools and Inspect | 0 | TRUE | 2025-12-05 08:00 | 2025-12-09 17:00 | Plastibell
18.02.003 Project Timeline.xml | 442 | Sample/Process Development | 0 | TRUE | 2025-12-10 08:00 | 2025-12-11 17:00 | Plastibell
18.02.003 Project Timeline.xml | 443 | Tool Adjustments (If needed) | 0 | TRUE | 2025-12-12 08:00 | 2025-12-16 17:00 | Plastibell
20250107-001 Full Schedule.xml | 2781 | NAMSA Evaluation | 30 | TRUE | 2025-08-25 08:00 | 2025-11-21 17:00
20250107-001 Full Schedule.xml | 605 | Prepare samples for biocomp | 0 | TRUE | 2025-11-24 08:00 | 2025-11-28 17:00 | Ref Medline 2x
20250107-001 Full Schedule.xml | 609 | Skin Sensitization (T0, 2x sterile) | 0 | TRUE | 2025-12-01 08:00 | 2026-02-06 17:00 | Quote Expedite Options, Nelson/Labcorp
20250107-001 Full Schedule.xml | 612 | Add biocomp results into existing BEFs | 0 | TRUE | 2026-02-09 08:00 | 2026-02-20 17:00 | Scope BEFs impacted
20250107-001 Full Schedule.xml | 3039 | Notify Regulatory of testing results | 0 | TRUE | 2026-02-23 08:00 | 2026-02-23 17:00
20250107-001 Full Schedule.xml | 59 | Required Notices/Release CMI, FDA, EU MDR, etc | 0 | TRUE | 2026-02-24 08:00 | 2026-03-23 17:00
20250107-001 Full Schedule.xml | 2879 | 076-264 Lustran 348 Pre-colored White | 0 | TRUE | 2027-12-01 08:00 | 2027-12-01 17:00
20250107-001 Full Schedule.xml | 2878 | 076-319 Lustran 348 Natural | 0 | TRUE | 2027-12-01 08:00 | 2027-12-01 17:00
20250107-001 Full Schedule.xml | 2667 |  | 0 | FALSE | 2024-12-16 08:00 | 2024-12-16 17:00
20250107-001 Full Schedule.xml | 1037 |  | 0 | FALSE | 2024-12-16 08:00 | 2024-12-16 17:00
QP 20250422-001 Project Schedule.xml | 495 | QP Approved | 0 | TRUE | 2025-04-22 08:00 | 2025-04-22 17:00
QP 20250422-001 Project Schedule.xml | 644 | Verify the scope of part # change at thinner supplier | 0 | TRUE | 2025-04-23 08:00 | 2025-07-29 17:00
QP 20250422-001 Project Schedule.xml | 642 | Receive Letter of Equivalency from TampoPrint | 0 | TRUE | 2025-07-30 08:00 | 2025-08-05 17:00
QP 20250422-001 Project Schedule.xml | 643 | Receive Letter of Equivalency from TampoPrint | 0 | TRUE | 2025-07-30 08:00 | 2025-08-05 17:00
QP 20250422-001 Project Schedule.xml | 648 | Project Delay | 0 | TRUE | 2025-08-06 08:00 | 2025-09-15 17:00
QP 20250422-001 Project Schedule.xml | 647 | Evaluate and update BEFs (change material # with equivalency letters) - Teams task | 0 | TRUE | 2025-09-16 08:00 | 2025-10-20 17:00
QP 20250422-001 Project Schedule.xml | 663 | Revise Purchase Specification to match new part # (on CN) - Ref Letters in content | 0 | TRUE | 2025-10-21 08:00 | 2025-12-08 17:00
QP 20250422-001 Project Schedule.xml | 657 | Formal notification to suppliers | 0 | TRUE | 2025-12-09 08:00 | 2025-12-09 17:00
QP 20250422-001 Project Schedule.xml | 666 |  | 0 | FALSE | 2025-04-22 08:00 | 2025-04-22 17:00
QP 20250422-001 Project Schedule.xml | 668 | QP Approved | 0 | FALSE | 2025-04-22 08:00 | 2025-04-22 17:00

## AllOpenActions
Project | TaskUID | TaskName | IsSummary | IsMilestone | PercentComplete | Active | Critical | Start | Finish | Notes | IsOpenAction
Schedule - Parker Laboratories Gel Packet.xml | 42 | Route VR for Bioburden (VR 9.0-221-01) for approval via Promotion Request | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-04 08:00 | 2025-11-10 17:00 | 8/1/2025: have continually reached out to Ronda to ask for updates. Also have communicated with Kasi regarding updates when she visited them. Parker has not sent any correspondance between December 2024 and July 16, 2025. New materials are set to release in October this year. I told Ronda we still needed the follwing (in black) from them to close out our documentation. Their responses are in RED. Responses from Candy at Parker (cbeck@parkerlabs.com) 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions. | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 132 | Route VR for Bioburden (PR 9.0-221-01) for approval via Promotion Request | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-04 08:00 | 2025-11-10 17:00 | 8/1/2025: have continually reached out to Ronda to ask for updates. Also have communicated with Kasi regarding updates when she visited them. Parker has not sent any correspondance between December 2024 and July 16, 2025. New materials are set to release in October this year. I told Ronda we still needed the follwing (in black) from them to close out our documentation. Their responses are in RED. Responses from Candy at Parker (cbeck@parkerlabs.com) 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions. | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 54 | Route VR (VR 9.0-221-02) for approval via Promotion Request | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-04 08:00 | 2025-11-10 17:00 | PR #: See note above for other VR 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions. | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 133 | Route VR (VR 9.0-221-02) for approval via Promotion Request | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-04 08:00 | 2025-11-10 17:00 | PR #: See note above for other VR 1. Burst testing validation report – We have done engineering feasibility testing to be sure the validation will pass, but have not completed the formal validation. That will be done on the first manufactured production batch in October. We will provide you with results from the formal validation. 2. Official statement of no functional product change I could say now that we don’t intend a functional change, but until the first production batch is tested, I would not make any official statements to customers. Once we have completed all testing, we will be happy to make this statement officially. 3. Bioburden test results We do have bioburden for the product we put on stability, but bioburden testing will be part of our production validation and I think that would be more relevant for demonstrating bioburden under normal manufacturing conditions. | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 125 | Create and release CN for gel packet | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-12-08 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 128 | Update Quality Records | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-11 08:00 | 2025-12-15 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 127 | Complete Quality Plan summary report | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-16 08:00 | 2026-01-12 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 129 | Release updated part (031002) via CN | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2026-02-02 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 130 | Release updated quality records via CN | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-13 08:00 | 2026-03-09 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 131 | Project Complete | FALSE | TRUE | 0 | TRUE | TRUE | 2026-03-09 17:00 | 2026-03-09 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 134 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2023-07-04 08:00 | 2023-07-04 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 136 | Create and release CN for gel packet | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-11-24 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 138 | Update Quality Records | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-11-24 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 139 | Complete Quality Plan summary report | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-27 08:00 | 2025-11-07 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 140 | Release updated part (031002) via CN | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-25 08:00 | 2025-12-22 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 141 | Release updated quality records via CN | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-27 08:00 | 2025-11-21 17:00 |  | TRUE
Schedule - Parker Laboratories Gel Packet.xml | 142 | Project Complete | FALSE | TRUE | 0 | TRUE | FALSE | 2025-12-22 17:00 | 2025-12-22 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 63 | 23 Weeks | FALSE | FALSE | 0 | TRUE | FALSE | 2025-06-11 08:00 | 2025-11-18 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 64 | 30 Weeks | FALSE | FALSE | 0 | TRUE | FALSE | 2025-06-11 08:00 | 2026-01-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 270 | Prototypes due to Exact Imaging (per PDA) | FALSE | TRUE | 0 | TRUE | FALSE | 2026-01-06 17:00 | 2026-01-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 353 | Prototype Review | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-07 08:00 | 2026-01-20 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 354 | Protoypes Approved By Exact Imaging (per PDA) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-21 08:00 | 2026-01-21 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 366 | Prep Prod Release | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-22 08:00 | 2026-02-18 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 367 | Production Released (per PDA) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-19 08:00 | 2026-02-19 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 835 | Plastibell Holiday Shut Down | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-22 08:00 | 2026-01-02 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 834 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-07 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 764 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-07 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 812 | Evaluate samples for damage | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-07 08:00 | 2025-08-07 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 813 | Ship samples to Plastibell | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-08 08:00 | 2025-08-12 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 814 | Identify if a tray is required to prevent damage when shipping | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-13 08:00 | 2025-08-13 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 815 | Approve Plastibell to design/purchase new tray | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-14 08:00 | 2025-08-14 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 816 | Update drawing or specification as needed | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-15 08:00 | 2025-08-21 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 821 | Duplicate inspection fixtures for Plastibell | FALSE | FALSE | 90 | TRUE | FALSE | 2025-08-05 08:00 | 2025-09-08 17:00 | Update start date to reflect actual. Update completion date. | TRUE
18.02.003 Project Timeline.xml | 403 | 134-200-1 Adj | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 404 | 134-200-2 Adj | FALSE | FALSE | 0 | TRUE | TRUE | 2025-10-21 08:00 | 2025-11-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 405 | 134-200-3 Adj | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 407 | Ship T2 Samples | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-07 08:00 | 2025-11-11 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 408 | T2 ES (Testing) | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-12 08:00 | 2025-11-18 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 409 | T2 Sample Approval | FALSE | TRUE | 0 | TRUE | TRUE | 2025-11-18 17:00 | 2025-11-18 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 411 | 134-200-1 | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 412 | 134-200-2 | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 413 | 134-200-3 | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-19 08:00 | 2025-12-04 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 416 | Receive Tools and Inspect | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-05 08:00 | 2025-12-09 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 442 | Sample/Process Development | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-10 08:00 | 2025-12-11 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 443 | Tool Adjustments (If needed) | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-12 08:00 | 2025-12-16 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 418 | Run OQ sample (30) | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-17 08:00 | 2025-12-18 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 445 | Ship to Coralville | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2025-12-23 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 444 | Approve OQ Samples | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-24 08:00 | 2025-12-24 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 419 | Approve OQ via inspection at Plastibell | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-19 08:00 | 2025-12-19 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 421 | Run PQ samples | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-22 08:00 | 2025-12-26 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 422 | Ship PQ samples to Coralville | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-29 08:00 | 2025-12-31 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 423 | PQ Functional Testing | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-01 08:00 | 2026-01-09 17:00 | CMM | TRUE
18.02.003 Project Timeline.xml | 424 | PQ Approval | FALSE | TRUE | 0 | TRUE | TRUE | 2026-01-09 17:00 | 2026-01-09 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 425 | Draft PE Form | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-01 08:00 | 2026-01-01 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 426 | Prototype Samples ship to Exact Imaging (Bear) | FALSE | TRUE | 0 | TRUE | FALSE | 2026-01-09 17:00 | 2026-01-09 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 427 | Ship Samples to Exact Imaging for Review/Approval | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-12 08:00 | 2026-01-13 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 428 | Sample Review/Approval | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-14 08:00 | 2026-01-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 429 | PPAP Package | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2026-01-08 17:00 | V&V Docs | TRUE
18.02.003 Project Timeline.xml | 430 | V&V Document Review | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-09 08:00 | 2026-01-15 17:00 | CV MFG ENG | TRUE
18.02.003 Project Timeline.xml | 433 | Route IOV | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-11 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 434 | Route VERP | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-11 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 435 | Route VER | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-12 08:00 | 2026-01-16 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 436 | Route VP | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-11 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 437 | Route VR | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-12 08:00 | 2026-01-16 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 438 | Route DHA | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-12 08:00 | 2026-01-16 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 752 | Route VVA | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-12 08:00 | 2026-01-16 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 439 | Update VMP | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-12 08:00 | 2026-01-12 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 628 | Design Transfer Review | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-19 08:00 | 2026-01-19 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 440 | Route CN for Production Release | FALSE | FALSE | 0 | TRUE | TRUE | 2026-01-20 08:00 | 2026-03-02 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 441 | CN for production release Implemented (Bear) | FALSE | FALSE | 0 | TRUE | TRUE | 2026-03-03 08:00 | 2026-03-03 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 833 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-07 08:00 | 2025-07-07 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 763 | Evaluate samples for damage | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-07 08:00 | 2025-08-07 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 762 | Ship samples to Plastibell | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-08 08:00 | 2025-08-12 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 759 | Identify if a tray is required to prevent damage when shipping | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-13 08:00 | 2025-08-13 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 758 | Approve Plastibell to design/purchase new tray | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-14 08:00 | 2025-08-14 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 757 | Update drawing or specification as needed | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-15 08:00 | 2025-08-21 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 645 | Duplicate inspection fixtures for Plastibell | FALSE | FALSE | 90 | TRUE | FALSE | 2025-08-11 08:00 | 2025-09-12 17:00 | Update start date to reflect actual. Update completion date. | TRUE
18.02.003 Project Timeline.xml | 706 | T1 ES and determine tool mods | FALSE | FALSE | 71 | TRUE | FALSE | 2025-10-01 08:00 | 2025-10-20 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 708 | 134-200-1 Adj | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 709 | 134-200-2 Adj | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 710 | 134-200-3 Adj | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-27 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 712 | Ship T2 Samples | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-28 08:00 | 2025-10-30 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 713 | T2 ES (Testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-31 08:00 | 2025-11-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 714 | T2 Sample Approval | FALSE | TRUE | 0 | TRUE | FALSE | 2025-11-06 17:00 | 2025-11-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 716 | 134-200-1 | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-07 08:00 | 2025-11-24 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 717 | 134-200-2 | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-07 08:00 | 2025-11-24 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 718 | 134-200-3 | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-07 08:00 | 2025-11-24 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 721 | Receive Tools and Inspect | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-25 08:00 | 2025-11-27 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 722 | Sample/Process Development | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-28 08:00 | 2025-12-01 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 723 | Tool Adjustments (If needed) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-02 08:00 | 2025-12-04 17:00 | Plastibell | TRUE
18.02.003 Project Timeline.xml | 725 | Run OQ sample (30) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-05 08:00 | 2025-12-08 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 726 | Ship to Coralville | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2025-12-11 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 727 | Approve OQ Samples | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-12 08:00 | 2025-12-12 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 728 | Approve OQ via inspection at Platibell | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2025-12-09 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 730 | Run PQ samples | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-10 08:00 | 2025-12-16 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 731 | Ship PQ samples to Coralville | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-17 08:00 | 2025-12-19 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 732 | PQ Functional Testing | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-22 08:00 | 2025-12-26 17:00 | CMM | TRUE
18.02.003 Project Timeline.xml | 733 | PQ Approval | FALSE | TRUE | 0 | TRUE | FALSE | 2025-12-26 17:00 | 2025-12-26 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 734 | Draft PE Form | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-22 08:00 | 2025-12-22 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 735 | Prototype Samples ship to Exact Imaging (Bull) | FALSE | TRUE | 0 | TRUE | FALSE | 2025-12-26 17:00 | 2025-12-26 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 736 | Ship Samples to Exact Imaging for Review/Approval | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-29 08:00 | 2026-01-01 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 737 | Sample Review/Approval | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-02 08:00 | 2026-01-15 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 738 | PPAP Package | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2025-12-29 17:00 | V&V Docs | TRUE
18.02.003 Project Timeline.xml | 739 | V&V Document Review | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-30 08:00 | 2026-01-05 17:00 | CV MFG ENG | TRUE
18.02.003 Project Timeline.xml | 831 | Pull 50 Samples from T2 build | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-31 08:00 | 2025-11-03 17:00 | Verify with Plastibell/Tool Maker | TRUE
18.02.003 Project Timeline.xml | 830 | Ship samples from PB-> JZ | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-04 08:00 | 2025-11-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 829 | Evaluate for damage | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-07 08:00 | 2025-11-10 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 832 | Update/release shipping specification | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-12-01 17:00 | TBD alignment internally (Include in Purchase Specification Template?) | TRUE
18.02.003 Project Timeline.xml | 742 | Route IOV | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-11 08:00 | 2025-08-15 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 743 | Route VERP | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-11 08:00 | 2025-08-15 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 744 | Route VER | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-29 08:00 | 2026-01-02 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 745 | Route VP | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-11 08:00 | 2025-08-15 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 746 | Route VR | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-29 08:00 | 2026-01-02 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 747 | Route DHA | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-29 08:00 | 2026-01-02 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 748 | Update VMP | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-06 08:00 | 2026-01-06 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 749 | Design Transfer Review | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-05 08:00 | 2026-01-05 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 750 | Route CN for Production Release | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-06 08:00 | 2026-01-26 17:00 |  | TRUE
18.02.003 Project Timeline.xml | 751 | CN for production release Implemented (Bull) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-27 08:00 | 2026-01-27 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 814 | TP Pivot Pro (TPPP) (104A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 813 | Verza (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 812 | Ultra-Pro II (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 811 | Exact Imaging TP Tower | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 810 | Exact Imaging Dual Path Guide | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 827 | Panasonic Integrated Guide (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1 | TRUE
20250107-001 Full Schedule.xml | 826 | Disposable Endoguide (102A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 1/2/3 | TRUE
20250107-001 Full Schedule.xml | 825 | Disposable Template Grid (301D) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 824 | Ultra-Pro III (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 823 | L25 (101B) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 822 | Infiniti Plus (101C) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 821 | Philips C10 Tracking Bracket (103A2) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 820 | Hitachi BX2 (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 819 | General Purpose Sensor (103A1) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 817 | Canon Integrated Guide (101A) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 2 | TRUE
20250107-001 Full Schedule.xml | 816 | AccuSITE (101B) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 3 | TRUE
20250107-001 Full Schedule.xml | 818 | omniTRAX (103C) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-01-03 08:00 | 2025-01-06 17:00 | Tier 3 | TRUE
20250107-001 Full Schedule.xml | 2567 | Ultra-Pro e (101C) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-03-03 08:00 | 2025-03-04 17:00 | Tier 3 | TRUE
20250107-001 Full Schedule.xml | 2590 | VirtuTRAX (103D) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-03-03 08:00 | 2025-03-04 17:00 | Tier 3 | TRUE
20250107-001 Full Schedule.xml | 2589 | eTRAX (103B) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-03-03 08:00 | 2025-03-04 17:00 | Tier 3 | TRUE
20250107-001 Full Schedule.xml | 59 | Required Notices/Release CMI, FDA, EU MDR, etc | FALSE | FALSE | 0 | TRUE | TRUE | 2026-02-24 08:00 | 2026-03-23 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2875 | CMI Registration/Ninsho Inclusion | FALSE | FALSE | 0 | TRUE | FALSE | 2026-03-24 08:00 | 2026-09-07 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3031 | FDA Registration Update | FALSE | FALSE | 0 | TRUE | FALSE | 2026-03-24 08:00 | 2026-04-20 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1002 | Develop Customer Communication/Notification Plan | FALSE | FALSE | 15 | TRUE | FALSE | 2025-08-25 08:00 | 2026-04-09 15:00 | Breakout by OEM affected as needed | TRUE
20250107-001 Full Schedule.xml | 1003 | Contract/SQA Implications | FALSE | FALSE | 0 | TRUE | FALSE | 2026-03-24 08:00 | 2026-04-13 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2776 | Tier 2 | FALSE | FALSE | 80 | TRUE | FALSE | 2025-08-19 08:00 | 2025-09-15 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2777 | Tier 3 | FALSE | FALSE | 15 | TRUE | FALSE | 2025-09-02 08:00 | 2025-09-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1167 | Tier 3 | FALSE | FALSE | 50 | TRUE | FALSE | 2025-07-29 08:00 | 2025-08-04 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2780 | Tier 3 | FALSE | FALSE | 50 | TRUE | FALSE | 2025-08-05 08:00 | 2025-11-10 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1073 | Ship parts to Coralville | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-11-17 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2803 | 2X Sterile | FALSE | FALSE | 50 | TRUE | FALSE | 2025-08-19 08:00 | 2025-11-10 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2804 | 2X Leak Testing (If Applicable) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-11-11 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 580 | BI testing (Product Sterility) | FALSE | FALSE | 60 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-30 17:00 | $1000/ea, 4 ea | TRUE
20250107-001 Full Schedule.xml | 581 | Update VR for PR 9.16 (BI testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-31 08:00 | 2025-10-31 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 582 | Pay Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-03 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 556 | BBMV - SGS (T0, 1x sterile) - Medline | FALSE | FALSE | 75 | TRUE | FALSE | 2025-09-23 08:00 | 2025-10-20 17:00 | SGS | TRUE
20250107-001 Full Schedule.xml | 558 | Update VR for PR 9.0-??? (BBMV) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-10-21 17:00 | Individual Device | TRUE
20250107-001 Full Schedule.xml | 559 | BBRM - SGS (T0, non-sterile) - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-21 08:00 | 2025-11-17 17:00 | Only Tier 1, hold parts per BBMV | TRUE
20250107-001 Full Schedule.xml | 561 | Update VR for PR 9.0-??? (BBRM) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-18 08:00 | 2025-11-18 17:00 | Individual Device | TRUE
20250107-001 Full Schedule.xml | 564 | Update VR for PR 9.0-??? (EO Residual) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-15 08:00 | 2025-10-15 17:00 | Individual Device Updates | TRUE
20250107-001 Full Schedule.xml | 567 | Update VR for PR 9.0-??? (B&F Sterility) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-08-26 17:00 | Individual Device Updates | TRUE
20250107-001 Full Schedule.xml | 2838 | ES Completion | FALSE | FALSE | 75 | TRUE | FALSE | 2025-09-26 08:00 | 2025-09-26 17:00 | Confirm completion date - Ally, Cristina | TRUE
20250107-001 Full Schedule.xml | 2823 | BI testing (Product Sterility) | FALSE | FALSE | 75 | TRUE | FALSE | 2025-09-01 08:00 | 2025-09-26 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2824 | Update VR for PR 9.16 (BI testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-29 08:00 | 2025-09-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2825 | Pay Steris | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-01 08:00 | 2025-09-01 17:00 | Steris team will absorb cost. | TRUE
20250107-001 Full Schedule.xml | 2827 | BBMV - SGS (T0, 1x sterile) - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-29 08:00 | 2025-08-25 17:00 | SGS | TRUE
20250107-001 Full Schedule.xml | 2828 | Update VR for PR 9.0-??? (BBMV) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-08-26 17:00 | Individual Device | TRUE
20250107-001 Full Schedule.xml | 2829 | BBRM - SGS (T0, non-sterile) - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-09-22 17:00 | Only Tier 1, hold parts per BBMV | TRUE
20250107-001 Full Schedule.xml | 2830 | Update VR for PR 9.0-??? (BBRM) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-23 08:00 | 2025-09-23 17:00 | Individual Device | TRUE
20250107-001 Full Schedule.xml | 2832 | EO Residual - Medline current cycle (T0, 2x sterile) | FALSE | FALSE | 75 | TRUE | FALSE | 2025-09-24 08:00 | 2025-10-14 17:00 | Only Tier 1 | TRUE
20250107-001 Full Schedule.xml | 2833 | Update VR for PR 9.0-??? (EO Residual) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-15 08:00 | 2025-10-15 17:00 | Individual Device Updates | TRUE
20250107-001 Full Schedule.xml | 2834 | B&F Sterility (T0, 1x sterile) - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-05 08:00 | 2025-08-25 17:00 | Only Tier 1 | TRUE
20250107-001 Full Schedule.xml | 2835 | Update VR for PR 9.0-??? (B&F Sterility) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-08-26 17:00 | Individual Device Updates | TRUE
20250107-001 Full Schedule.xml | 2864 | MEA (2X sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-01 08:00 | 2025-09-26 17:00 | 3x per device (134-209) per material | TRUE
20250107-001 Full Schedule.xml | 2865 | Doc Updates (VR) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-16 08:00 | 2025-10-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 537 | T=0 Functional Testing (UPII) | FALSE | FALSE | 90 | TRUE | FALSE | 2025-08-08 08:00 | 2025-09-04 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 538 | T=0 Functional Testing (Endoguide) | FALSE | FALSE | 90 | TRUE | FALSE | 2025-08-08 08:00 | 2025-09-04 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2810 | T0 Testing Complete (Tier 1) | FALSE | TRUE | 0 | TRUE | FALSE | 2025-09-04 17:00 | 2025-09-04 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2807 | Receive Parts from Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-13 08:00 | 2025-08-19 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3032 | Delay due to testing capacity (not necessary for project success) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-12-15 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2806 | T0 Testing (Tier 2) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-16 08:00 | 2026-02-02 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2805 | Receive Parts from Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-12 08:00 | 2025-11-18 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2808 | T0 Testing (Tier 3) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-03 08:00 | 2026-03-02 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 548 | Kitting for Ship Testing - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-15 08:00 | 2025-12-16 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2809 | Coordinate testing with DDL | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-17 08:00 | 2025-12-19 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 551 | Send product to DDL | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-22 08:00 | 2025-12-23 17:00 | Service Provider | TRUE
20250107-001 Full Schedule.xml | 552 | Ship Testing - DDL (T0, 2x sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-24 08:00 | 2026-01-27 17:00 | cost per load $4800, plan 2 loads | TRUE
20250107-001 Full Schedule.xml | 1084 | Receive at CV2 | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-28 08:00 | 2026-01-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 553 | Post-Ship Functional Testing | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-30 08:00 | 2026-02-12 17:00 | Partial Functional Testing | TRUE
20250107-001 Full Schedule.xml | 554 | Update VR for PR 9.0-6 (ship testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-13 08:00 | 2026-02-19 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 555 | Update VR for PR 9.0-49 & PR 9.0-28 (ship testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-13 08:00 | 2026-02-19 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3068 | Kitting for Ship Testing - Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-12 08:00 | 2026-02-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3069 | Coordinate testing with DDL | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-06 08:00 | 2026-02-10 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3070 | Send product to DDL | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-11 08:00 | 2026-02-12 17:00 | Service Provider | TRUE
20250107-001 Full Schedule.xml | 3071 | Ship Testing - DDL (T0, 2x sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-13 08:00 | 2026-03-19 17:00 | cost per load $4800, plan 2 loads | TRUE
20250107-001 Full Schedule.xml | 3072 | Receive at CV2 | FALSE | FALSE | 0 | TRUE | FALSE | 2026-03-20 08:00 | 2026-03-23 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3073 | Post-Ship Functional Testing | FALSE | FALSE | 0 | TRUE | FALSE | 2026-03-24 08:00 | 2026-04-06 17:00 | Partial Functional Testing | TRUE
20250107-001 Full Schedule.xml | 3074 | Update VR for PR 9.0-6 (ship testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-07 08:00 | 2026-04-07 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3075 | Update VR for PR 9.0-49 & PR 9.0-28 (ship testing) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-07 08:00 | 2026-04-07 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2781 | NAMSA Evaluation | FALSE | FALSE | 30 | TRUE | TRUE | 2025-08-25 08:00 | 2025-11-21 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2867 | NAMSA Evaluation Invoice | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-24 08:00 | 2025-11-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 605 | Prepare samples for biocomp | FALSE | FALSE | 0 | TRUE | TRUE | 2025-11-24 08:00 | 2025-11-28 17:00 | Ref Medline 2x | TRUE
20250107-001 Full Schedule.xml | 607 | Cytotoxicity (T0, 2x sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-01 08:00 | 2025-12-26 17:00 | Quote Expedite Options, Nelson/Labcorp | TRUE
20250107-001 Full Schedule.xml | 609 | Skin Sensitization (T0, 2x sterile) | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-01 08:00 | 2026-02-06 17:00 | Quote Expedite Options, Nelson/Labcorp | TRUE
20250107-001 Full Schedule.xml | 611 | Intracutneous Injection (T0, 2x sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-01 08:00 | 2026-01-02 17:00 | Quote Expedite Options, Nelson/Labcorp | TRUE
20250107-001 Full Schedule.xml | 610 | Invoice Nelson/Labcorp | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-05 08:00 | 2026-01-05 17:00 | Consider GLP | TRUE
20250107-001 Full Schedule.xml | 612 | Add biocomp results into existing BEFs | FALSE | FALSE | 0 | TRUE | TRUE | 2026-02-09 08:00 | 2026-02-20 17:00 | Scope BEFs impacted | TRUE
20250107-001 Full Schedule.xml | 3039 | Notify Regulatory of testing results | FALSE | FALSE | 0 | TRUE | TRUE | 2026-02-23 08:00 | 2026-02-23 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3040 | 134-209 T3 AA | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-26 08:00 | 2025-12-18 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 601 | MEA T=0 (Medline) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2026-01-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 602 | LAL T=0 (Medline) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2026-01-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1095 | MEA T=3 (Medline) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2026-01-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1096 | LAL T=3 (Medline) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-19 08:00 | 2026-01-29 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 603 | Update VR for PR 9.0-209-01 & PR 9.0-209-02 (MEA & LAL) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-30 08:00 | 2026-02-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1082 | GP Sensor received | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2025-12-09 17:00 | Need to add lead time for NDI conversion | TRUE
20250107-001 Full Schedule.xml | 1081 | eTRAX received | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-11 08:00 | 2025-11-11 17:00 | Needle is sterile, sensor is non-sterile | TRUE
20250107-001 Full Schedule.xml | 1080 | omniTRAX received | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-10 08:00 | 2025-12-10 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1083 | Exernal validation | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-11 08:00 | 2025-12-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1086 | Ship to Nelson | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2025-12-11 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1093 | Manual Cleaning Validation | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-12 08:00 | 2026-02-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1085 | LLD | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-12 08:00 | 2026-02-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1087 | Simulated Use | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2026-01-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 624 | Prepare Samples | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-06 08:00 | 2026-02-19 17:00 | Katie to advise on sample parts required | TRUE
20250107-001 Full Schedule.xml | 625 | Chemical compatibility for disposable parts and report writing | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-06 08:00 | 2026-02-12 17:00 | Confirm Timeline | TRUE
20250107-001 Full Schedule.xml | 1077 | Chemical compatibility for reusable parts | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-20 08:00 | 2026-04-16 17:00 | Confirm Timeline | TRUE
20250107-001 Full Schedule.xml | 626 | Cleaning | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-20 08:00 | 2026-04-23 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 627 | LLD (Low level disinfection) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-02-20 08:00 | 2026-04-23 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 628 | Invoice Nelson | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-24 08:00 | 2026-04-24 17:00 | $10K LLD + $6K Cleaning | TRUE
20250107-001 Full Schedule.xml | 98 | Gate 2 - Review V&V results | FALSE | TRUE | 0 | TRUE | FALSE | 2026-04-27 08:00 | 2026-04-27 17:00 | Review gate review checklist for PDP and reference for Sustaining Gate Review. | TRUE
20250107-001 Full Schedule.xml | 76 | Update affected IOV's - Remove reference to material | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-28 08:00 | 2026-05-11 17:00 | Complete before Functional Testing Starts | TRUE
20250107-001 Full Schedule.xml | 77 | Update affected VER | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-12 08:00 | 2026-05-25 17:00 | Verification Report | TRUE
20250107-001 Full Schedule.xml | 142 | Update affected VERP | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-12 08:00 | 2026-05-25 17:00 | Complete before Functional Testing Starts | TRUE
20250107-001 Full Schedule.xml | 2783 | Update affected VP | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-12 08:00 | 2026-05-25 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2782 | Update affected VR | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-12 08:00 | 2026-05-25 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 78 | Update affected DHA | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-12 08:00 | 2026-05-25 17:00 | Design History File Audit | TRUE
20250107-001 Full Schedule.xml | 143 | Update affected DMR's | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-28 08:00 | 2026-05-11 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 79 | Update Production Routers | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-28 08:00 | 2026-05-11 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2870 | Update VMPs | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-24 08:00 | 2026-01-13 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 81 | Drawing Updates | FALSE | FALSE | 0 | TRUE | FALSE | 2026-04-27 08:00 | 2026-05-22 17:00 | Wait until post ABS-Decon? | TRUE
20250107-001 Full Schedule.xml | 2876 | CMI Confirms new resin acceptability | FALSE | FALSE | 0 | TRUE | FALSE | 2026-09-08 08:00 | 2026-09-08 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 82 | Release CN's | FALSE | FALSE | 0 | TRUE | FALSE | 2026-09-09 08:00 | 2026-10-06 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 100 | Gate 3 Review | FALSE | FALSE | 0 | TRUE | FALSE | 2026-10-07 08:00 | 2026-10-07 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1039 | Earliest Plastibell Run-out | FALSE | FALSE | 0 | TRUE | FALSE | 2025-04-25 08:00 | 2025-04-25 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1040 | Earliest Guttenberg Run-out | FALSE | FALSE | 0 | TRUE | FALSE | 2025-06-12 08:00 | 2025-06-12 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2655 | TPPP Order Date | FALSE | FALSE | 0 | TRUE | FALSE | 2026-10-01 08:00 | 2026-10-01 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2654 | TPPP Inventory Run-out | FALSE | FALSE | 0 | TRUE | FALSE | 2027-01-01 08:00 | 2027-01-01 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2879 | 076-264 Lustran 348 Pre-colored White | FALSE | FALSE | 0 | TRUE | TRUE | 2027-12-01 08:00 | 2027-12-01 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2878 | 076-319 Lustran 348 Natural | FALSE | FALSE | 0 | TRUE | TRUE | 2027-12-01 08:00 | 2027-12-01 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1046 | Qual / V&V | FALSE | FALSE | 0 | TRUE | FALSE | 2025-02-24 08:00 | 2025-02-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1045 | NPD 1000027372 Production Release | FALSE | FALSE | 0 | TRUE | FALSE | 2025-05-12 08:00 | 2025-05-12 17:00 | 1000027372 | TRUE
20250107-001 Full Schedule.xml | 1048 | Qual / V&V | FALSE | FALSE | 0 | TRUE | FALSE | 2025-02-24 08:00 | 2025-02-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1047 | NPD 1000029543 Production Release | FALSE | FALSE | 0 | TRUE | FALSE | 2025-05-12 08:00 | 2025-05-12 17:00 | 1000029543 | TRUE
20250107-001 Full Schedule.xml | 3076 | TP Direct | FALSE | FALSE | 0 | TRUE | FALSE | 2026-05-05 08:00 | 2026-05-05 17:00 | Plastibell | TRUE
20250107-001 Full Schedule.xml | 2667 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2024-12-16 08:00 | 2024-12-16 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 1037 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2024-12-16 08:00 | 2024-12-16 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3037 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2024-12-16 08:00 | 2024-12-16 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3025 | Mold Samples (GP Sensor) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-22 08:00 | 2025-11-14 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2914 | Ship GP Sensor to NDI | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-17 08:00 | 2025-11-19 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2915 | NDI Conversion | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-20 08:00 | 2025-12-03 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3033 | Complete Testing Scope | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-17 08:00 | 2025-11-17 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2916 | NDI Testing | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-04 08:00 | 2025-12-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2917 | Ship to CV2 | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-04 08:00 | 2025-12-08 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3034 | External Validation | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2026-01-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3035 | Internal Verification (Sensor Positioning) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-09 08:00 | 2026-01-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2918 | eTRAX | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-10-20 17:00 | Dependent on medical grade colorant | TRUE
20250107-001 Full Schedule.xml | 2919 | omniTRAX | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-10-20 17:00 | Dependent on medical grade colorant | TRUE
20250107-001 Full Schedule.xml | 2920 | virtuTRAX | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-10-20 17:00 | Dependent on medical grade colorant | TRUE
20250107-001 Full Schedule.xml | 2923 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2924 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2925 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2926 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2927 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2928 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2929 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2930 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2931 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2932 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 2933 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2934 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2935 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2936 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2937 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2938 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2939 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2940 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2941 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2942 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2943 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2944 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2945 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2946 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-22 08:00 | 2025-09-04 17:00 | Cycolac HMG47MD (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 2947 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2948 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2949 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2950 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-10-02 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2953 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2954 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2955 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2956 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2957 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2958 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2959 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2960 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2961 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2962 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 2963 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2964 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2965 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2966 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2967 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2968 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2969 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2970 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2971 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2972 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2973 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2974 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2975 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2976 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-05 08:00 | 2025-09-18 17:00 | Cycolac HMG47MD (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 2977 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2978 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2979 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2980 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-10-16 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3024 | Scope biocomp testing per NAMSA Evaluation | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-03 08:00 | 2025-11-27 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3011 | Determine Adoption/Test Plan | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-28 08:00 | 2025-12-04 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 2982 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2983 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2984 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2985 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2986 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2987 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2988 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2989 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2990 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2991 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 2992 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2993 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2994 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2995 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Lustran 348MX | TRUE
20250107-001 Full Schedule.xml | 2996 | Polar White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2997 | Marine Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2998 | Pale Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 2999 | Fuchsia (Pink) - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3000 | Fuchsia (Pink) - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3001 | Light Grey - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3002 | Clariant Black - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3003 | White - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3004 | Teal Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3005 | Black - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-19 08:00 | 2025-09-19 17:00 | Cycolac HMG47MD (GP Sensor) | TRUE
20250107-001 Full Schedule.xml | 3006 | Royal Blue - Compound | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3007 | Citrus - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3008 | Mid Blue - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3009 | Spearmint Green - Colorant | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-17 08:00 | 2025-10-17 17:00 | Cycolac HMG47MD | TRUE
20250107-001 Full Schedule.xml | 3036 | Mold Rep Sample ahead of NAMSA testing | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-26 08:00 | 2025-08-26 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3027 | Placeholder | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-11-07 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3016 | Schedule 302 SWOs | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-10 08:00 | 2025-11-28 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3017 | Complete 302 SWOs | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-01 08:00 | 2025-12-05 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3018 | Sterilize (2X) Medline | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-08 08:00 | 2025-12-26 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3012 | Complete Functional Testing T0 (Non-Sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-12-29 08:00 | 2026-01-02 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3013 | Complete Functional Testing T0 (2X Sterile) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-05 08:00 | 2026-01-09 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3014 | Complete Functional Testing T3 (AA) | FALSE | FALSE | 0 | TRUE | FALSE | 2026-01-12 08:00 | 2026-04-06 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3019 | Scope Impacted DHF documents | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-10-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3020 | Revise Scoped DHF Docs | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-27 08:00 | 2025-11-21 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3021 | Update Drawings (post deconstruction) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-20 08:00 | 2025-10-24 17:00 |  | TRUE
20250107-001 Full Schedule.xml | 3022 | CN for release (if applicable) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-24 08:00 | 2025-12-19 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 495 | QP Approved | FALSE | FALSE | 0 | TRUE | TRUE | 2025-04-22 08:00 | 2025-04-22 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 644 | Verify the scope of part # change at thinner supplier | FALSE | FALSE | 0 | TRUE | TRUE | 2025-04-23 08:00 | 2025-07-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 642 | Receive Letter of Equivalency from TampoPrint | FALSE | FALSE | 0 | TRUE | TRUE | 2025-07-30 08:00 | 2025-08-05 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 643 | Receive Letter of Equivalency from TampoPrint | FALSE | FALSE | 0 | TRUE | TRUE | 2025-07-30 08:00 | 2025-08-05 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 648 | Project Delay | FALSE | FALSE | 0 | TRUE | TRUE | 2025-08-06 08:00 | 2025-09-15 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 646 | Write memo to capture why V&V not required (include emails from ITW Transtech) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-06 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 664 | Update QPSR (Note why EI is not notified, Letters with emails, etc) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 665 | Create FA's for 1st Production | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 647 | Evaluate and update BEFs (change material # with equivalency letters) - Teams task | FALSE | FALSE | 0 | TRUE | TRUE | 2025-09-16 08:00 | 2025-10-20 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 650 | TPPP (134-233) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 651 | TP Tower (134-200) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 652 | Cryo Grid (134-109) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 653 | 17GA Grid (134-114) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 654 | 18GA Grid (134-115) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 655 | Verza Guide (034-229) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-13 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 663 | Revise Purchase Specification to match new part # (on CN) - Ref Letters in content | FALSE | FALSE | 0 | TRUE | TRUE | 2025-10-21 08:00 | 2025-12-08 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 657 | Formal notification to suppliers | FALSE | FALSE | 0 | TRUE | TRUE | 2025-12-09 08:00 | 2025-12-09 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 666 |  | FALSE | FALSE | 0 | TRUE | FALSE | 2025-04-22 08:00 | 2025-04-22 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 668 | QP Approved | FALSE | FALSE | 0 | TRUE | FALSE | 2025-04-22 08:00 | 2025-04-22 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 670 | Verify the scope of part # change at thinner supplier | FALSE | FALSE | 0 | TRUE | FALSE | 2025-04-23 08:00 | 2025-07-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 671 | Receive Letter of Equivalency from TampoPrint | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-30 08:00 | 2025-08-05 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 672 | Receive Letter of Equivalency from TampoPrint | FALSE | FALSE | 0 | TRUE | FALSE | 2025-07-30 08:00 | 2025-08-05 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 673 | Project Delay | FALSE | FALSE | 0 | TRUE | FALSE | 2025-08-06 08:00 | 2025-09-15 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 674 | Write memo to capture why V&V not required (include emails from ITW Transtech) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-22 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 675 | Update QPSR (Note why EI is not notified, Letters with emails, etc) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 676 | Create FA's for 1st Production | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 677 | Evaluate and update BEFs (change material # with equivalency letters) - Teams task | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-10-10 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 679 | TPPP (134-233) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 680 | TP Tower (134-200) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 681 | Cryo Grid (134-109) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 682 | 17GA Grid (134-114) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 683 | 18GA Grid (134-115) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 684 | Verza Guide (034-229) | FALSE | FALSE | 0 | TRUE | FALSE | 2025-09-16 08:00 | 2025-09-29 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 685 | Revise Purchase Specification to match new part # (on CN) - Ref Letters in content | FALSE | FALSE | 0 | TRUE | FALSE | 2025-10-13 08:00 | 2025-10-31 17:00 |  | TRUE
QP 20250422-001 Project Schedule.xml | 687 | Formal notification to suppliers | FALSE | FALSE | 0 | TRUE | FALSE | 2025-11-03 08:00 | 2025-11-03 17:00 |  | TRUE